MVP Development Plan: AI Engineering Systems

Project Title: Self-Improving Prompt & Intelligent Context Engineering Systems

Team: E M Mohammed Sinan 1, Nandu Soman V T 2, Jaswin Jose 3, Abraham Jacob Pathil 4, Karthik Nair 5

Date: September 13, 2025

Duration: 8 Weeks

### 1.0 Team Roles

| Team Member | Assigned Project | Role |
| --- | --- | --- |
| E M Mohammed Sinan | Project PromptEvolve | AI Architect |
| Jaswin Jose | Project PromptEvolve | ML Engineer (Evaluation & Metrics) |
| Nandu Soman V T | Project ContextCore | Data Engineer |
| Abraham Jacob Pathil | Project ContextCore | Systems Engineer (Integration & Deployment) |
| Karthik S Nair | Both Projects | Integration & QA Engineer |

### 2.0 8-Week Efficient Project Plan

#### Weeks 1-2: Foundation & Scaffolding

- E M Mohammed Sinan (PromptEvolve):

  - Design the core architecture and data structures for the
 PromptEvolution framework.

  - Build the skeleton for the
 EvolutionEngine and
 PromptChallengerclasses.

- Jaswin Jose (PromptEvolve):

  - Define the class structures for the
 PromptSolver and
 PromptVerifier

  - Implement a basic, default evaluation function for initial testing.

- Nandu Soman V T (ContextCore):

  - Design the Python architecture for the multi-source context retrieval pipeline.

  - Define the data structures for handling context from different sources (e.g., Graphiti, LightRAG).

- Abraham Jacob Pathil (ContextCore):

  - Set up the Git repository with a clear directory structure for both projects.

  - Create mock JSON data files to simulate the outputs from Graphiti, LightRAG, and the Task Management system.

- Karthik S Nair (Integration):

  - Define and finalize the YAML configuration schema for both projects.

  - Build a basic CLI (Command Line Interface) with argparse to run placeholder functions.

#### Weeks 3-4: Core Logic Implementation

- E M Mohammed Sinan (PromptEvolve):

  - Implement the prompt variation generation logic within the
 PromptChallenger, including strategies like chain-of-thought and few-shot examples14.

  - Develop the main evolution loop in
 evolve_prompts15.

- Jaswin Jose (PromptEvolve):

  - Implement the
 PromptSolver to execute prompts against test cases loaded from the YAML config16.

  - Build out the
 PromptVerifier with domain-specific evaluation metrics17.

- Nandu Soman V T (ContextCore):

  - Implement the Context Optimization Engine, focusing on relevance scoring 18, deduplication 19, and token budget management20.

- Abraham Jacob Pathil (ContextCore):

  - Build robust Python "connector" modules that read and parse the mock data files.

  - Create initial Dockerfiles for both projects to containerize the environments.

- Karthik S Nair (Integration):

  - Write unit tests for the YAML parsing logic.

  - Expand the CLI to fully run the prompt evolution loop for a specified domain.

#### Weeks 5-6: Integration & End-to-End Flow

- E M Mohammed Sinan & Jaswin Jose (PromptEvolve):

  - Integrate a live LLM API client into the PromptChallenger and PromptSolver.

  - Perform the first end-to-end run of the prompt evolution system, debugging the flow from generation to selection.

- Nandu Soman V T & Abraham Jacob Pathil (ContextCore):

  - Integrate the data connector modules into the main context assembly pipeline21.

  - Implement context personalization based on user role and preferences defined in the YAML config.

- Karthik S Nair (Integration):

  - Write integration tests for the complete workflows of both systems.

  - Update the CLI to execute the context assembly pipeline from Project ContextCore.

#### Weeks 7-8: Refinement, Analytics & Documentation

- E M Mohammed Sinan (PromptEvolve):

  - Implement prompt lineage tracking to log the history of prompt evolution for analytics23.

  - Refine the evolution engine based on test results.

- Jaswin Jose (PromptEvolve):

  - Implement the
 Prompt Performance Analytics module to calculate and log success metrics24.

- Nandu Soman V T (ContextCore):

  - Implement a simple context caching mechanism to improve performance.

  - Build out the context quality assessment feedback loop.

- Abraham Jacob Pathil (ContextCore):

  - Finalize Dockerfiles and create a docker-compose.yml for easy one-command setup.

  - Write README.md files with clear setup and execution instructions for both projects.

- Karthik S Nair (Integration):

  - Finalize the CLI with comprehensive help messages and user instructions.

  - Create a master README.md for the entire repository and perform final QA testing.

### 3.0 Initial Execution Steps

To begin immediately, the team should follow these steps in order:

- Project Kickoff & Git Setup (Day 1):

  - Action: Abraham will initialize the shared GitHub repository and add all team members as collaborators.

  - Action: The team will hold a 1-hour kickoff meeting to agree on the Git workflow (e.g., feature branches, pull request reviews) and communication tools.

- Finalize YAML Schema (Day 1-2):

  - Action: Karthik will create a document defining the proposed YAML structure for configuring both systems.

  - Action: All team members must review the schema and provide feedback. This schema must be approved by the end of Day 2 as it is a dependency for all modules.

- Environment Configuration (Day 2-3):

  - Action: All team members will set up their local Python environments (venv or conda), clone the repository, and ensure they can run a basic main.py file.

  - Action: Abraham will commit the initial Dockerfile and requirements.txt to the repository.

- Commence Scaffolding Sprint (Day 3):

  - Action: All team members begin the tasks outlined in the "Weeks 1-2" plan, starting with creating the empty Python files and class definitions for their assigned modules.

- Establish Daily Stand-ups (Ongoing):

  - Action: The team will establish a daily 15-minute stand-up call to discuss progress, current tasks, and any blockers. This ensures continuous alignment and rapid problem-solving.